## Feature List
FEATURE | BREAKDOWN | PRIORITY | STATUS | To complete by | Helpful links
Turret Rotation | Up, Down (with limit) | HIGH | DONE
| Left, Right (360 rotation) |  | DONE
Camera Zoom | Pinch to zoom in/out | HIGH | DONE
Lock-On to Target | Button that locks on to a target | MEDIUM
When reticle hovers over a person, another reticle will appear on the person to show that lock on can be activated
Switch Lock-On Target | Button that switches lock on target to next nearest lock-on target | MEDIUM |  |  | https://www.youtube.com/watch?v=C6GqSTS3ghM
| Player can manipulate the direction at which their next lock-on target will be at by draggin the directional controls | LOW
Profile Scan | Button that scans target who's locked on | HIGH |  | today
| Once scanned, a window will open up in the UI containing profile of scanned target | HIGH |  | today
| Profile View does not pause game | LOW |  | today
Profile | Based on who/what is scanned: |  |  | today
| > Bandits/Raiders | POSTPONED | DELAY
| > Civilians/Warden/Police | MEDIUM |  | today
Randomizes persons identity into the category
| > Identitiy = name, criminal record, clothes they spawn in | MEDIUM
Shoot Weapon/Turret | Button that fires weapon | HIGH | DONE
| Charging mechanic (allows for stronger output) | POSTPONED | DELAY
Weapon Switch | Switch weapon types: | POSTPONED | DELAY
| > Precision laser | POSTPONED | DELAY
| > Sniper Bullet Physical Rounds | POSTPONED | DELAY
| > High-Explosive Energy Beam | POSTPONED | DELAY
| > High-Explosive Physical Rounds | HIGH | DONE
Bullet Physics | Gravity | MEDIUM | DONE
| Wind | POSTPONED | DELAY
Spin-drift
Temperature
Humidity
Map + Assets | Walls around the city | HIGH | DONE
| Tower | HIGH | DONE
| Turret on Tower |  | DONE
| Cameras | MEDIUM | DONE
| Terrain | HIGH | DONE
| Houses | HIGH | DONE
| Civilian | MEDIUM |  | today
NPCs | NPC Model | LOW
| Auto movement |  | DONE
Randomized profiles
| Animations | POSTPONED | DELAY
| NPC Spawn |  | DONE
Story | In-between mission dialogue | HIGH |  | today
| During-mission dialogue | POSTPONED | DELAY
UI | Pause Button |  | DONE
| Resume Button |  | DONE
| Quit Game Button |  | DONE
| Scan Button | HIGH | DONE
| Lock On Button | HIGH | DONE
| Reticle UI | HIGH |  | today
Audio | SFX + BGM + etc | POSTPONED | DELAY
| > Menu UI button clicks | POSTPONED | DELAY
| > In game UI button clicks | POSTPONED | DELAY
| > Weapon fire sound | POSTPONED | DELAY
| > Explosion from weapon sound | POSTPONED | DELAY
| > People screaming sound | POSTPONED | DELAY
| > Zooming sound | POSTPONED | DELAY
| > Scanning sound | POSTPONED | DELAY
Android Build | Prep for android use | HIGH | DONE
| Final Build | VERY HIGH

## Priority List
TOP PRIORITY
Shoot button | DONE
Rotation | DONE
Civilians with nav-mesh | DONE
Roads + City buildings | DONE
MEDIUM PRIORITY
Lock On
Randomized Civilian Profiles
Scan Civilian Profile
Aim Zoom
Turret + Tower + Wall art assets
Switch between Cameras
Switch between different Towers
LOW PRIORITY